## ✅
0/62 completed
✓ | Date | Task
FALSE | STAGE 1 | Pre-Planning
FALSE |  | Choose your team by appointing a move manager.
FALSE |  | Discuss your available budget and ideal time frame.
FALSE |  | Coordination between the old and new leases. TIP: How much notice do you have to give your landlord? Minimise double rent.
FALSE |  | Have you started the recruitment process if you need more staff?
FALSE |  | TIP: Send a questionnaire to your team members and see what works well in your current space, what doesn't and what you can do to make the new space even better! (CLICK link for survey download)
FALSE |  | Choose an area, how are the transport routes, parking, access, etc. Is this area inline with your company image?
FALSE |  | Collate above data and start to form your brief, the document that states your operational and key requirements.
FALSE | STAGE 2 | Find your place
FALSE |  | Contact some commercial landlords.
FALSE |  | TIP: Don't just choose the top 4 or five on Google ( this just means that they pay the most for their clicks) choose on actual user reviews. + learn the difference between an office broker and a commercial estate agent.
FALSE |  | Consider your fees: Rental deposit on new property Professional fees: (commercial property agent, legal, insurance) Office Design & Fit-Out of new property
FALSE |  | Set aside adequate time to schedule the viewings, pack them in more the merrier!
FALSE |  | Make a list of questions to ask the estate agent + take the summary from your staff questionnaires to see if you can visualise these within the spaces.
FALSE |  | Take pictures of each site you visit and request plans of the space to keep track of what was where.
FALSE |  | TIP: Note how you feel in the spaces. You and your team will be spending a lot of time in these new spaces. How are the sound levels, natural light what direction are the windows facing ( due south is best )
FALSE |  | Book a pre-lease feasibility study with a design company. TIP: This inexpensive service will help you to avoid any pitfalls or spaces that are expensive to convert. We have found that this service has helped our clients save thousands on spaces that look right but have hidden implications when converting. Is the property listed etc... do you have conversion restrictions... are all typical examples of this service.
FALSE | STAGE 3 | Stay on top of the tasks
FALSE |  | Summarise your visits, rate them and take pictures so you can later discuss with the team.
FALSE |  | Keep staff regularly involved in the process & informed about the process & the progress.
FALSE |  | TIP: Negotiate terms also think of the future, how will the landlord expect you to leave the space after your lease is up? Many companies overlook this costly requirement.
FALSE |  | Ask your legal representative to summarise the main lease terms, if you are unhappy then ask for amendments.
FALSE |  | Negotiate hard, then make offers and carefully check heads of terms. Ask for an exclusivity agreement so the property is taken off the market.
FALSE |  | Review of timescales with all move suppliers.
FALSE | STAGE 4 | Choose a design company
TIP: To get the best for your space you need it to do 3 main things 1. Reinforce your brand, ethos and vision to your team and visitors. ( Smart businesses leverage their space as selling tool and to unite their teams, when the team are aligned magic things happen! ) 2. Function extremely well in terms of productivity, ease of use and practicality. 3. Be a space that your team really enjoy spending time in, have their needs met and gives them areas for work, rest, socialisation and rejuvenation. ( Our numerous case studies show that when a space is designed with these key components productivity rises, employee retention and consequently profit. )
FALSE |  | Make an inventory of your current furniture, speak to your design company to plan for any more needed for the move.
FALSE |  | Look at the space pragmatically, how is the security? Are their any restrictions with access?
FALSE |  | Contact your services
FALSE |  | IT and internet
FALSE |  | Phone lines
FALSE |  | Waste collection
FALSE |  | Cleaning and maintenance
FALSE |  | Utilities ( if not included )
FALSE |  | Insurances need to be updated and reissued to new space
FALSE |  | TIP: How are the car parking requirements? Your removal company will need the access to make the process quick and easy
FALSE | STAGE 5 | One step ahead
FALSE |  | Contact removal companies, again go for ones with the best actual client reviews.
FALSE |  | Contact Post Office and arrange for mail to be forwarded to your new address.
FALSE |  | TIP: Recheck your timings with the teams, does this move clash with any launches or industry specific events.
FALSE |  | Make an inventory of all your equipment.
FALSE |  | Let your customers and your suppliers know you are moving.
FALSE |  | TIP: DECLUTTER This is a great time to declutter your space, if its not being used then think 'will we need this in our new space'. There are some really good companies out there that will repurpose your old furniture and this too reduces waste sent to landfill. Some will even buy it from you.
FALSE | STAGE 6 | Prepare to NOT fail
FALSE |  | Decide how you will move? Will it be done in stages with key teams moved over later once the new space is up and running or all in one go?
FALSE |  | Confirm the below: 🗹
FALSE |  | Review of timescales, with all move suppliers.
FALSE |  | New suppliers, phone lines, IT, utilities, waste collection, cleanin
FALSE |  | Access and parking booked for current and new space. TIP: Can you block off the lift for your sole use to speed up the move? All hands on deck.
FALSE |  | TIP: Make a schedule of condition for the new office on arrival, take plenty of photographs and note any damage to the space before you move in. Once completed walk around with the property agent and get this signed off for mutual peace of mind.
FALSE |  | Start to pack 📦
FALSE |  | Your removal company should provide storage crates for personal items that can be labelled.
FALSE |  | Teamwork! Encourage your teams to give a hand moving is very labour intensive so if everybody lends a hand you will save time and external labour costs.
FALSE |  | Create a moving office plan and schedule that everybody can follow. TIP: A calender or gaant chart would work best, diarise the main steps, WHO, WHAT and WHEN so everybody is accountable and in the loop.
FALSE |  | Build in a contingency plan and some room to 'breathe'. With the best planning sometimes things take a little longer so give your self space to react.
FALSE | STAGE 7 | I like to move it move it
FALSE |  | Make the move fun, order refreshments and maybe play some music.
FALSE |  | TIP: Check that the essentials work: keys, alarms and do you have a fire evacuation plan?
FALSE |  | Plan the work and then work the plan! Stay organised : Tick off stages of completion and put the stages on the clock.
FALSE |  | Update your literature, email signatures, letter heads etc, business cards, website & marketing material , etc. to your new address.
FALSE | STAGE 8 | Time to celebrate 🎉
FALSE |  | Plan the formal moving in party. This is a great opportunity to promote your brand to your potential clients, show that you have expanded via social media and create some news! TIP: take lots of selfies🤳 but don't forget to enjoy yourself and be present!
FALSE
FALSE
FALSE
FALSE
This check list is an essentials guide to the main steps your appointed Design and fit out company will be able to streamline this process and create the necessary links to services and contractors that can give you a hand. *******************************************************************************************

## TEMPL
| Moving Office Checklist | 64/0 completed
✓
STAGE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE